## V0
| Month | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
| Week start | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
| Project week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Integration:
1a | Teleoperation
1b | Reference processing
1c | Impact/contact monitoring
1d | RS QP control
Research:
2a | Passive impact absorption
2b | Contact monitoring
2c | Data collection
Miscelaneous:
Finish report draft
Report finalizing
Prepare presentation
Buffer
[13 empty] | Break (TBD) | [22 empty] | Break

## V1
| Month | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
| Week start | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
| Project week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Integration:
1a | Teleoperation | bar: 2022-05-09 to 2022-05-30
1b | Reference processing | bar: 2022-05-30 to 2022-06-13
1c | Impact/contact monitoring | bar: 2022-06-13 to 2022-07-11
1d | RS QP control | bar: 2022-08-15 to 2022-09-12
Research:
2a | Passive impact absorption | bar: 2022-05-09 to 2022-06-13
2b | Contact monitoring | bar: 2022-06-13 to 2022-07-11
2c | Data collection | bar: 2022-10-10 to 2022-10-17
Miscelaneous:
Finish report draft | bar: 2022-10-24 to 2022-11-14
Report finalizing | bar: 2022-11-21 to 2022-12-05
Prepare presentation | bar: 2022-12-12 to 2022-12-19
Buffer | bar: 2022-09-19 to 2022-10-03; 2023-01-09 to 2023-01-30
[13 empty] | Break (TBD) | [22 empty] | Break

## V2
|  | Month | May |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | Februari
|  | Week start | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27
|  | Project week | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
Integration:
1a | 100% | Teleoperation with QP | [41 empty] | 0 | 2006-12-01 | Progress meeting 13 | bar: 1899-12-31 to 1900-01-05
1b | 100% | Reference processing | [41 empty] | 1 | 2012-12-01 | Submit draft for initial feedback | bar: 1900-01-06 to 1900-01-10
1c | 100% | Impact/contact monitoring | [41 empty] | 2 | 2019-12-01 | Receive initial feedback Jari | bar: 1900-01-08 to 1900-01-10; 1900-01-15 to 1900-01-18
1d | 100% | RS QP control | [41 empty] | 3 | 2016-01-01 | Submit draft for final feedback | bar: 1900-01-18
|  | Research: | [41 empty] | 4 | 2030-01-01 | Receive final feedback
2a | 100% | Passive impact absorption | [41 empty] | 5 | 2006-02-01 | Submit final report | bar: 1900-01-02 to 1900-01-09
2b | 100% | Contact monitoring | [41 empty] | 6 | 2020-02-01 | Approximate target for defense | bar: 1900-01-10; 1900-01-15 to 1900-01-17
|  | Miscelaneous: | [42 empty] | 2005-03-01 | Ultimate deadline defense
Final data collection
|  | Finish report draft | [42 empty] | While waiting for feedback:
|  | Finish final draft | [42 empty] | work on presentation or video
Finish final report
Prepare presentation
Make video
|  |  | 1900-01-11: Break | [12 empty] | Break
[31 empty] | 0 | 1 | 2 | Break |  |  | 3 |  | 4 | 5 |  | 6